## Sheet1
Changes/Updates to protoype catalog display
ID | Description | From | Date | On | Priority | Comment | Status
#001 | I think we need a Legend/Key/Guide to explain the columns and how the measurements were made. Maybe for this we will pick a 'demo HI CME image' and draw PA lines on it with the overlaid coordinate grid. | JB | 2015-03-20 | JAD JB DB | High | Fully agree. We probably need both a short description which can appear at the top of the catalogue page and then a more in depth description which can be on separate page and which can address any caveats, version release notes etc. | Open
#002 | Can the PA range bar scale in units of 5 to match our measurements? Maybe it and the "Date range" boxes can be better aligned. | JB | 2015-03-20 | CHP | Medium | Done | Closed
#003 | Can we display a more human readable form of the Data&Time online, and leave the formal version in the data files? Maybe just remove the T and Z. (Note the spacing of this font a little inconsistent, most obviously around the number 1.) | JB | 2015-03-20 | CHP | Medium | A quick fix has been applied to the catalogue to show what the output would looklike without the CSSDS delimiters. This is useful as it will load directly into Excel. A better solution will be to have the option to display both as sugegsted by Jackie in #007. There are a couple of issues with the fonts, one is a general issue that the current font does not scale nicely at the default zoom level; the other is whether we should use a monospace font for the table. | Open
#004 | The LT and GT columns confuse things (presuming those are LessThan/GreaterThan binaries). If possible, I would suggest having the actual symbol of </> in with the PA value. | JB | 2015-03-20 | tbd | Medium | Yes the LT and GT fields were extracted from the greater/less than information in the catalogue. For the time being these columns. are hidden but a better solution is required. There are a number of possible options but it is worth to bear in mind that annotation of numeric fields is generally a bad idea and web pages/XML encode angle brackets (since they are reserved characters) and this can cause issues when copy/pasting the contents from the web page. One option is to use "<" & ">" in the current LT/GT fields. Another option is that we have a separate flags field which incorporates this information. | Open
#005 | I'm not sure we can/should use the word "Halo". I know we want to indicate something to that effect, but it's a questionable nomenclature in the HI observations. Maybe rename that column to "Potential Halo" and list yes/no instead of Halo/no. Or avoid "Halo" altogether and maybe we can brainstorm something like (field-of-view) "FOV Event" or "Width > FOV" or ">FOV Limits" or similar... | JB | 2015-03-20 | DB CHP | Medium | The intention is to remove this field from the source catalogue. For now the column has been hidden so that it is not displayed by default. | Open
#006 | I'm also not sure about the "Quality" index. As far as I'm concerned these are all CMEs (the 2s are just prettier and more obvious than the 1s), and quality implies a measure of good/bad data or observations which isn't a quantified parameter, just a subjective label. I worry that it will always be a cause for less fruitful debate, and even confuse users. If we included 0s I would understand a need for some confidence classification, but otherwise I hesitate to include it. Actually I might be happier with, for example, "Good" in place of 2 and "Fair" in place of 1 (the removed 0s being "Poor" say). We might even put an option in to allow a user to 'opt in' to see Poor events, but default not to display them. | JB | 2015-03-20 | DB | Medium | The poor qulaity events are not included in the source catalogue provided by David. The numeric values have been modified to show 'Good' and 'Fair' on the web site. This should be implemented in the source catalogue so that users will see the same thing if they download the catalogue or view it on the web site. | Open
#007 | For time, we could add a “use CCSDS” keyword (to put T and Z back in for download purposes - to facilitate ease of reading). | JAD | 2015-03-20 | CHP | Medium | This looks like a good approach | Open
#008 | Change column titles for PA which currently say 'PA Min' and 'PA Max' whereas acording to Jackie description is should be North and South | CHP | 2015-03-20 | CHP | High | Done | Closed
#009 | Extend column titles to include units etc. | CHP | 2015-03-20 | CHP | High |  | Open
#010 | Activate the date selection option | CHP | 2015-03-20 | CHP | High | Done | Closed
#011 | Include a PA width selection option | CHP | 2015-03-20 | CHP | Medium | Done | Closed
#012 | Change the PA selection to be based on the mid-PA value and not the limits | JAD | 2015-03-20 | CHP | Medium | Done | Closed
#013 | Change PA selection so that separate sliders are provided for East and West and have a check box to lock values (the default option) | CHP | 2015-03-23 | CHP | Medium | The current 0-360 PA selection does not allow users to pick similar range in East and West directions which might be useful when trying to match CMEs. | Open
#014 | Provide a link to the STEREO orbit page | JAD | 2015-03-23 | CHP | Medium | It has been verified that this can be done with a IRL of the form http://stereo-ssc.nascom.nasa.gov/cgi-bin/make_where_gif?day=20&month=04&year=2008&hour=05&minute=10 so this is certainly possible. | Open
#015 | Identify other links/images/resources that should be linked to individual events. | CHP | 2015-03-23 | All | Medium | It would be good to collect this information so that we can decided the best way to incorporate into the web site. | Open
#016 | Change single record selection to multiple record selection | CHP | 2015-03-23 | CHP | Low | Currently the table is set for single row selection however it would be more useful to allow multiple selections (which is easy). This will then allow selected records to be copied and would also allow the linked information to be quickly stepped through for the selected events. | Open
#017 | Consider possibility of providing option to display old versions of the catalogue | CHP | 2015-03-23 | CHP | Low | Not important for now but could be useful if/when we start to release new versions and users want to be able to idetify the changes. | Open
#018 | Extend catalogue to cover additional years | CHP | 2015-05-23 | DB JB | High | We would like to have as broad coverage as we can in time for the open meeting | Open