| Title: | HELCATS 18 Month Report Nov. 2015 (Part A) |
| --- | --- |
| Document Number: | HELCATS_STFC_D1_5_1 |
| Project Deliverable: | D1.5 |
| Release/Date | Version: 0.2 2015-11-10 |
| Editor: | Richard Harrison, Jackie Davies, Jason Byrne |
| Contributors: | HELCATS Consortium |
| Reviewed By: | HELCATS Steering Committee |
| Distribution: | EU & PROJECT |

Document Information:

# Revision History

| - Issue | - Date | - Lead Author | - Comments |
| --- | --- | --- | --- |
| - 1.0 | 2015-10-01 | - Richard Harrison, Jackie Davies, Jason Byrne (STFC) | - Initial release |

# Acronym List

AMDA 		Automated Multi-Dataset Analysis (software tool)

CIR 		Co-rotating Interaction Region

CME 		Coronal Mass Ejection

CNRS 		Centre National de la Recherche Scientifique

EUV 		Extreme UltraViolet

GCS		Graduated Cylindrical Shell model

GMU 		George Mason University

HELCATS 	Heliospheric Cataloguing, Analysis and Techniques Service

HI 		Heliospheric Imager/Imaging

ICME		Interplanetary CME

IMPERIAL 	Imperial College of Science, Technology and Medicine, London

IPR 		Intellectual property rights

IPS 		Interplanetary Scintillation

MGT 		Management

MHD 		Magnetohydrodynamics

ROB 		Koninklijke Sterrenwacht van Belgie

RTD 		Research and Technology Development

RAL 		Rutherford Appleton Laboratory

OTH 		Other

SIR		Stream Interaction Regions

STEREO 		Solar Terrestrial Relations Observatory (mission)

STFC 		Science and Technology Facilities Council

TCD 	The Provost, Fellows, Foundation Scholars & the other members of Board of the College of the Holy and Undivided Trinity of Queen Elizabeth near Dublin

UGOE 		Georg-August-Universitaet Goettingen Stiftung Oeffentlichen Rechts

UH 		Helsingin Yliopisto

UNIGRAZ 	Universitaet Graz

UPS 		Universite Paul Sabatier Toulouse III

WP 		Work Package

# Table of Contents

PART A

Revision History	2

Acronym List	2

Table of Contents	3

INTRODUCTION	4

DELIVERABLES	9

# PART B

work package summaries and reports	9

Work Package 1 (WP1) - Management…………………………………………………………………………………………………9

Work Package 2 (WP2) - Producing a Definitive Catalogue of CMEs Imaged by STEREO/HI………………..11

Work Package 3 (WP3) - Deriving/cataloguing the kinematic properties of STEREO/HI CMEs based on geometrical and forward modelling…………………………………………………………………………………………………..16

Work Package 4 (WP4) - Verifying the Kinematic Properties of STEREO/HI CMEs Against In-situ CME Observations and Coronal Sources…………………………………………………………………………………………………….22

Work Package 5 (WP5) - Producing a Definitive Catalogue of CIRs Imaged by STEREO/HI that Includes Verified Model-Derived Kinematic Properties……………………………………………………………………………………27

Work Package 6 (WP6) - Initialising Advanced Numerical Models Based on the Kinetic Properties of STEREO/HI CMEs and CIRs …………………………………………………………………………………………………………………30

Work Package 7 (WP7) - Assessing the Complementary Nature of Radio Measurements of Solar Wind Transients………………………………………………………………………………………………………………………………………….33

Work Package 8 (WP8) - Dissemination…………………………………………………………………………………………….35

PROJECT summary	37

# Introduction

The advent of wide-angle imaging of the inner heliosphere has revolutionised the study of the solar wind and, in particular, transient solar wind structures such as Coronal Mass Ejections (CMEs) and Co-rotating Interaction Regions (CIRs). CMEs comprise enormous plasma and magnetic field structures that are ejected from the Sun and propagate at what can be immense speeds through interplanetary space, whilst CIRs are characterised by extensive swathes of compressed plasma/magnetic field that form along flow discontinuities of solar origin that permeate the inner heliosphere. With Heliospheric Imaging (HI) came the unique ability to track the evolution of these features as they propagate through the inner heliosphere. Prior to the development of wide-angle imaging of the inner heliosphere, signatures of such solar wind transients could only be observed within a few solar radii of the Sun, and in the vicinity of a few near-Earth and interplanetary in-situ probes. HI has, for the first time, filled that vast and crucial observational gap.

The HELCATS project provides an unprecedented focus for world-leading European expertise in the novel and revolutionary, European-led field of HI, in terms of instrumentation, data analysis, modelling and science. HELCATS is a strategic project that empowers the wider scientific community, in Europe and beyond, by providing access to advanced catalogues - validated and augmented through the use of techniques and models - for the analysis of solar wind transients, based on observations from European-led space instrumentation. All beneficiaries are at the forefront of heliospheric research and bring distinct, yet highly complementary, skills to the project. HELCATS adds significant value to the exploitation of existing European space instrumentation, providing a strong foundation for enhanced exploitation and advancement of European heliospheric research.

HELCATS recognises the synergy between solar and heliospheric physics research (both of which are European strengths) and their applied space weather aspect, currently a topic of vigorous debate in many political and scientific arenas. With the impending development of a European space weather capability, HELCATS has real, practical relevance.

The HELCATS consortium is led by STFC’s Rutherford Appleton Laboratory. The Coordinator is Professor Richard A Harrison, the Scientific Manager is Dr Jackie A Davies and the Technical Manager is Dr Jason P Byrne. The list of beneficiaries is given in Table 1. The HELCATS workpackage (WP) structure is given in Table 2.

Table 1:  HELCATS Beneficiaries

| No | NAME | SHORT NAME | COUNTRY |
| --- | --- | --- | --- |
| 1 | SCIENCE AND TECHNOLOGY FACILITIES COUNCIL | STFC | United Kingdom |
| 2 | UNIVERSITAET GRAZ | UNIGRAZ | Austria |
| 3 | UNIVERSITE PAUL SABATIER TOULOUSE | UPS | France |
| 4 | GEORG-AUGUST-UNIVERSITAET GOETTINGEN STIFTUNG OEFFENTLICHEN RECHTS | UGOE | Germany |
| 5 | KONINKLIJKE STERRENWACHT VAN BELGIE | ROB | Belgium |
| 6 | IMPERIAL COLLEGE OF SCIENCE, TECHNOLOGY AND MEDICINE | IMPERIAL | United Kingdom |
| 7 | HELSINGIN YLIOPISTO | UH | Finland |
| 8 | THE PROVOST, FELLOWS, FOUNDATION SCHOLARS & THE OTHER MEMBERS OF BOARD OF THE COLLEGE OF THE HOLY & UNDIVIDED TRINITY OF QUEEN ELIZABETH NEAR DUBLIN | TCD | Ireland |

Table 2:  The HELCATS WP structure

| WP No | WP ACTIVITY TYPE | WP TITLE |
| --- | --- | --- |
| 1 | MGT | MANAGEMENT |
| 2 | RTD | PRODUCING A DEFINITIVE CATALOGUE OF CMES IMAGED BY STEREO/HI |
| 3 | RTD | DERIVING/CATALOGUING THE KINETIC PROPERTIES OF STEREO/HI CMES BASED ON GEOMETRICAL AND FORWARD MODELLING |
| 4 | RTD | VERIFYING THE KINEMATIC PROPERTIES OF STEREO/ HI CMES AGAINST IN-SITU CME OBSERVATIONS AND CORONAL SOURCES |
| 5 | RTD | PRODUCING A DEFINITIVE CATALOGUE OF CIRS IMAGED BY STEREO/HI THAT INCLUDES VERIFIED MODEL- DERIVED KINEMATIC PROPERTIES |
| 6 | RTD | INITIALISING ADVANCED NUMERICAL MODELS BASED ON THE KINETIC PROPERTIES OF STEREO/HI CMES AND CIRS |
| 7 | RTD | ASSESSING THE COMPLEMENTARY NATURE OF RADIO MEASUREMENTS OF SOLAR WIND TRANSIENTS |
| 8 | OTHER | DISSEMINATION |

This 18 month report is broken down into reports from each WP. Thus, to aid the reading of these WP reports, we repeat the WP strategy and structure details here, and refer the reader to the WP structure diagram.

The fundamental aim of the HELCATS project is to start with heliospheric imaging observations and, from that, build up facilities, methods and assessment studies in a logical programme of activities. The work is managed by STFC, involving a total of eight European research groups. The activities of the groups are tailored to their scientific and technical strengths, maximizing the potential scientific return for the project.

WP1: Management - The consortium includes 8 European groups from 7 EU countries and 2 third parties. The project coordinates work involving observations, cataloguing, modelling, and studies in validation and assessment. WP1 covers the formal management roles of the HELCATS project. This includes administrative tasks, maintaining project infrastructure, coordinating inputs and reporting as required and handling a range of project issues. WP1 oversees the website production and management.

WP2: Producing a definitive catalogue of CMEs imaged by STEREO/HI - This WP provides the foundation for this project (including scientific coordination), namely the production of a catalogue of CMEs in the heliosphere. The catalogue is produced from manual inspection of STEREO/HI data but use of automated techniques are being investigated. Comparisons with coronal CME catalogues are being made.

WP3: Deriving/cataloguing the kinematic properties of STEREO/HI CMEs based on geometrical and forward modelling - Here we apply recently established geometrical, forward and (prototype) inverse modelling methods to derive CME parameters, which will be added to the catalogue (including back- and forward-projections to ‘predict’ CME launch and arrivals at various solar system locations). Comparisons will be made between the parameters yielded by the different models.

WP4: Verifying the kinematic properties of STEREO/HI CMEs against in-situ CME observations and coronal sources - This WP catalogues in-situ CME information (at Earth and elsewhere) for comparison to the projected data from WP3 in order to assess the performance of the aforementioned models. Similarly, comparisons are made with solar ‘surface’ phenomena. These allow a thorough validation of the models.

WP5: Producing a definitive catalogue of CIRs imaged by STEREO/HI that includes verified model-derived kinematic properties - In parallel with the CME cataloguing, modelling and model assessment in WP2-4, this WP performs an analogous activity for CIRs, again with cataloguing, geometrical modelling and the validation of results through comparisons to in-situ/solar data.

WP6: Initialising advanced numerical models based on the kinematic properties of STEREO/HI CMEs and CIRs - This WP recognises the potential for using HI data as input to numerical MHD models of the heliosphere (in terms of both CME and CIR phenomena) by considering the use of HI images for initialisation/driving of the ENLIL model. The results will be compared to traditional methods for running such models, based on coronal and photospheric inputs, to assess their potential.

WP7: Assessing the complementary nature of radio measurements of solar wind transients - WP7 explores the value of incorporating radio observations, to augment the HI data. It assesses the value of using interplanetary scintillation (IPS) observations and Type II radio burst data in conjunction with HI data, both of which can provide additional information.

WP8: Dissemination - WP8 brings the results to the community through (1) the publication of results in the open, refereed literature, (2) the running of annual open meetings, (3) the installation of all relevant documentation, catalogues and reports on the website and (4) the dissemination of information to the public and policy makers. This includes ingestion of the products into the AMDA data-mining tool the IRAP (UPS) propagation tool, and integration with projects such as HELIO. This WP coordinates the exploitation of the project outputs, such that they feed into numerous research activities and future space weather applications.

Overall, the HELCATS strategy is to coordinate a range of observational and modelling studies of heliospheric phenomena to provide a foundation for enhancing the scientific discipline and the exploitation of European investment in the hardware involved.

Full details of the HELCATS project can be seen in the description of work documents (606692_DOW_PART_A.pdf and 606692_DOW_PARTB.pdf) agreed with the European Commission in early 2014. The project kicked-off in May 2014. The distribution of work, divided by beneficiary and by WP is given in Table 3.

Table 3:  The distribution of work between beneficiaries and WP

| Beneficiary | WP1 | WP2 | WP3 | WP7 | WP4 | WP5 | WP6 | WP8 | Total per Beneficiary |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 – STFC | 8.50 | 25.00 | 9.00 | 19.50 | 0.00 | 0.00 | 0.00 | 11.50 | 73.50 |
| 2 - UNIGRAZ | 0.00 | 0.00 | 6.00 | 0.00 | 30.00 | 0.00 | 0.00 | 0.00 | 36.00 |
| 3 – UPS | 0.00 | 0.00 | 0.00 | 0.00 | 2.00 | 25.00 | 24.00 | 10.00 | 61.00 |
| CNRS | 0.00 | 0.00 | 0.00 | 0.00 | 2.00 | 8.00 | 3.00 | 0.00 | 13.00 |
| 4 – UGOE | 0.00 | 6.00 | 21.00 | 0.00 | 12.00 | 0.00 | 0.00 | 0.00 | 39.00 |
| 5 – ROB | 0.00 | 20.50 | 0.00 | 3.00 | 6.00 | 0.00 | 0.00 | 0.00 | 29.50 |
| 6 - IMPERIAL | 0.00 | 0.00 | 0.00 | 17.00 | 3.00 | 0.00 | 0.00 | 0.00 | 20.00 |
| 7 – UH | 0.00 | 0.00 | 0.00 | 0.00 | 13.00 | 9.00 | 0.00 | 0.00 | 22.00 |
| 8 – TCD | 0.00 | 0.00 | 15.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 15.00 |
| Total | 8.50 | 51.50 | 51.00 | 39.50 | 68.00 | 42.00 | 27.00 | 21.50 | 309.00 |

In the following pages we address each WP in turn, providing a summary of the WP activities and an update of progress and next steps. HELCATS is a three-year project and we are 18 months into the activities. The project has a clearly defined schedule of activities, milestones and deliverables and this report demonstrates that the project is on schedule. The WP summaries have been produced by the WP leaders; this does mean that the reports vary slightly in style and format. However, the aim is to produce a thorough statement on the status of the project and the future steps, and this, we believe has been done effectively.

# Deliverables List

| Del. no. | Deliverable name | WP no. | Nature | Dissemination level | Status |
| --- | --- | --- | --- | --- | --- |
| 1.1 | HELCATS Website | 1 | O | PU | Delivered month 3 |
| 1.2 | Minutes of Kick-off Mtg | 1 | R | PP | Delivered month 4 |
| 8.4 | Posting information on the website as appropriate (continuous process from stated delivery date) | 8 | O | PU | Delivered month 4 |
| 8.6 | Production of press releases, public talks (as appropriate – starting in month 4 at kick off) | 8 | O | PU | Delivered month 4 |
| 1.3 | Progress report to Commission | 1 | R | PP | Delivered month 7 |
| 2.1 | Catalogue of observational parameters of HI-1 manually-identified CMEs (first release month 9 and continuously updated as data permits). To be made available online. | 2 | O | PU | Delivered month 9 with ongoing updates |
| 2.2 | Report on the feasibility of automatic identification of CMEs in HI-1 data, leading to (if successful) the generation of a catalogue (made available online) of automatically-identified CMEs. | 2 | R | PP | Delivered month 12 |
| 3.1 | Provide time-elongation maps for the CMEs n the STEREO/HI catalogue (from WP2) and incorporate the results of the geometrical fitting into the catalogue (first release month 12, update as data permit) | 3 | O | PU | Delivered month 12 with ongoing updates |
| 3.2 | Incorporate the results of the forward-modelling techniques into the CME catalogue established in WP2 (first release, month 12, update as data permit) | 3 | O | PU | Delivered month 12 with ongoing updates |
| 5.1 | Establish an online CIR catalogue, including solar source, HI and in-situ data (first release month 12, update as data permits) | 5 | O | PU | Delivered month 12 with ongoing updates |
| 8.2 | Annual open meeting | 8 | O | PU | Months 12,24,36 |
| 8.3 | Attendance/presentations at major science meetings (e.g. EGU, AGU) (months are nominal) | 8 | O | PU | Months 12,24,36 |
| 1.4 | Project cost statements and annual progress report to commission – Year 1 | 1 | R | PP | Month 13 |
| 2.3 | Report on the inter-comparison of the manual and automated CME catalogues | 2 | R | PP | Month 18 |
| 1.5 | Progress report to Commission | 1 | R | PP | Month 19 |
| 4.1 | Establishing an online catalogue of potentially associated solar source and in-situ phenomena for the timeframe 2007-2015 | 4 | O | PU | Month 24 |
| 2.4 | Report in which the manual and automated HI CME catalogues are compared to pre-existing coronagraph CME catalogues. | 2 | R | PP | Month 24 |
| 1.6 | Project cost statements and annual progress report to commission – Year 2 | 1 | R | PP | Month 25 |
| 7.1 | Catalogues of EISCAT and LOFAR IPS data events and of S/WAVES events, both extending throughout the STEREO HI Mission timeline | 7 | O | PU | Month 27 |
| 7.2 | Report of initial comparison between IPS events and HI events | 7 | R | PP | Month 30 |
| 7.3 | Report of initial comparison between solar radio-burst events and HI events | 7 | R | PP | Month 30 |
| 4.2 | Report on statistical analysis and comparison of HI results with coronal and in situ data; assessment of forecasting accuracy | 4 | R | PP | Month 30 |
| 1.7 | Progress report to Commission | 1 | R | PP | Month 31 |
| 3.3 | Report on model results | 3 | R | PP | Month 36 |
| 3.4 | Report on prototype inverse model, basing on photospheric and low corona source region characteristics, for 3D CME structure for HI CME event | 3 | R | PP | Month 36 |
| 5.2 | Report on the statistical analysis and comparison of HI results with coronal and in situ data; assessment of forecasting accuracy of CIRs | 5 | R | PU | Month 36 |
| 6.1 | Online catalogue of the calibrated coronal input boundaries as well as a database of the most accurate simulations of background solar wind, CMEs and shocks in the ecliptic plane only. | 6 | O | PU | Month 36 |
| 6.2 | Report on the assessment of the use of HI data in numerical modelling of solar transients | 6 | R | PP | Month 36 |
| 8.5 | Integration with community facilities and websites | 8 | O | PU | Month 36 |
| 1.8 | Project cost statements and annual progress report to commission – Year 3 | 1 | R | PP | Month 37 |
| 1.9 | Final public report | 1 | R | PU | Month 38 |