WORK PACKAGE 5 (WP5): PRODUCING A DEFINITIVE CATALOGUE OF CIRs IMAGED BY STEREO/HI THAT INCLUES VERIFIED MODEL-DERIVED KINEMATIC PROPERTIES

WP5 ACTIVITY TYPE: UPS

WP5 DURATION: MONTHS 1 – 36

WP5 LEAD BENEFITIARY: STFC (1)

WP5 LEADER: Dr Alexis Rouillard

WP5 CONTRUBUTORS: UH (7)

WP5 OVERVIEW: The primary goal of WP5 is to provide a catalogue of the spatial and temporal evolution of Stream Interaction Regions (SIRs) observed by HI (and their substructures) in 3-D, following their complete formation process using different observations (mainly imaging but also insitu) from the Sun out to 1 AU. The output of the solar wind stream advanced catalogue will be optimized to help the space physics community in the search for clues on the origin, propagation, 3D morphology, and the planetary effects of CIRs and the slow solar wind.

We have addressed a large subset of the goals of the four tasks defined for WP5, namely: TASK 5.1: Cataloguing the occurrence of CIRs [Months: 1-36] (LEAD:UPS) - Using J-maps and optimized running-difference images, we will list the times of observations of each CIR in HI images [Done] - From the CIR fitted trajectories, we will provide a catalogue of the arrival times of CIRs at Mercury, Venus, Mars, Earth, Saturn, thereby providing support to European-funded space missions around these planets [Done for STEREO-A]. TASK 5.2: Deriving/cataloguing the kinematic variation of CIRs [Months: 1-24] (LEAD:UPS) - We will fit the leading edge of each CIR in HI J-maps derived at all available latitudes to obtain the spatial/temporal evolution of each CIR over ~180o longitude [Done for STEREO-A] and ~90o latitude [In process] TASK 5.3: Comp. back-projected CIR tracks with coronal sources [Months: 1-36] (LEAD:UPS) - Using the derived trajectories and kinematic properties of CIRs and their small-scale transients, we will determine for each CIR observed in white-light images if there is an associated coronal hole observed in EUV [Done for STEREO-A]. TASK 5.4- Comparing forward-projected CIR tracks with in-situ measurements [Months: 1-36] (LEAD:UPS) - We will track small-scale transients to 1 AU and make a list of predicted impacts at points in the heliosphere where in-situ measurements are taken [Done for STEREO-A, ACE, WIND and STEREO-B]. More detailed summary for Task 5.1, Task 5.2, Task 5.3 and Task 5.4: Using J-maps derived from running-difference images, Illya Plotnikov (recruited in May 2014) has listed the times of passage of each Corotating Density Structures (CDS) in the field of view of HI images obtained from STEREO-A (Goal 1 in T5.1). We then used our technique to determine the location of each CDS in the ecliptic plane as a function of time. In order to determine the time-dependent evolution of the 3-D trajectory of each SIR, the characteristic tracks left by these SIRs in the J-maps were fitted manually by clicking on J-maps produced with HI-1 and HI-2 images from STEREO-A (and in the future STEREO-B). For each SIR, we fitted first the clearest tracks associated with individual density irregularities entrained by the SIR. We then used the fact that a SIR corotates during its passage in the heliospheric imagers, thereby leaving a characteristic pattern in the J-map. This pattern was then computed theoretically and superposed onto the real J-map. The algorithm to trace this SIR pattern folds in a correction for the orbital motion of the spacecraft. This orbital motion changes the location of the viewpoint of the probe (STEREO-A) and can have an important effect when the SIR pattern is considered over a 180o of corotation in the HI field of view lasting up to 18 days. To validate a fitting we use two criteria (1) we require that the correspondence between the simulated and measured SIR patterns are satisfactory, (2) we require that the fitting technique (‘fixed-point technique’) of the trajectory of individual small-scale transients entrained by the SIR gives small errors in both speed (<40 km/s) and direction (<20o). Both of these criteria usually impose that the SIR be well observed by the heliospheric imagers over a large range of elongations (>40 degrees). CDSs that are poorly observed because (1) the white-light signature is too weak, (2) too many CMEs passed in the field of view are not fitted. Once a SIR is fitted, we assign it a time that corresponds to the launch time of the small-scale transient entrained by the SIR that is best observed during the event. We adopted this definition of the onset time because it guarantees that if a future user wishes to find this SIR in the heliospheric imagers, the single feature will be most easily spotted as a bright signature in the images (especially with the ‘propagation tool’: c.f. WP8 for more details). The Carrington longitude and latitude of the source region of the SIR was also recorded and was systemically compared with EUV images. For each event, we recorded whether a coronal hole was present less than 20o of longitudinal separation to the East of the SIR source region and recorded its location in Carrington coordinates (Goals 1 and 2 of T5.3). The format of the catalogue is given in the annual report. Since the annual report, Illya Plotnikov has completed the entire catalogue of CDSs from STEREO-A (2007-May 2014). He has compared the catalogue with various sets of in-situ measurements taken by STEREO-A, ACE/Wind and STEREO-B at the predicted times of impact of the CDS. The comparison shows that the fitted CDSs have speeds close to the slow solar wind speed and not the speed of the stream interface measured in situ. He has also demonstrated that CDSs are mostly S/CIRs and that all S/CIRs are detected by HI during the solar minimum period but at solar maximum the large number of CMEs passing in the field of view prevents the identification of half of the passing S/CIRs. He has also demonstrated that CDSs occur mostly at sector boundaries in situ and at the neutral line at the Sun (see Figure 5.1) and therefore the close relation between CDSs and small transients expelled in the palsma sheet. All these findings are included in a paper that will be soon submitted : Plotnikov, I., Rouillard, A.P., Davies, J.A. et al., Long-term tracking of corotating density structures using heliospheric imaging, to be submitted to Solar Physics, 2015. Illya has also investigated the possibility of fitting CDS in STEREO-B heliospheric images, however this is very difficult because the pattern left by the passage of CDSs in STEREO-B images is less clear. He has therefore developped a new scheme that is based on the STEREO-A fitting. He predicts the pattern of CDSs from STEREO-A to STEREO-B by letting the structure corotate in HI1-/2B, if the pattern generated in STEREO-B is reproduced, then a CDS is validated in that field of view. So we are deriving a new CDS catalogue for STEREO-B based on the STEREO-A catalogue. Upcoming updates: Illya is now investigating the effect of spacecraft motion which was recently demonstrated by Conlon et al (2015) to affect fitted speeds by a few tens of km/s. An updated CDS catalogue will be produced including spacecraft motion. Future deliverables (Due month 24) include the fitting of the leading edge of CIRs and determination of their latitudinal extend. Figure 5.1 A series of stack plots derived from measurements of the near-Earth plasma (panels a-c) and of the solar magnetic field using a PFSS model (panels e-g). All Stack plots are presented in the same way, with Carrington longitudes running along the X-axis and Carrington Rotation numbers along the Y-axis. The red diamonds are the estimated Carrington rotation number versus longitude of each CDS fitted in our catalogue. All measurements refer to magneto-plasma parameters (described in detail in the body of the article). Time runs from high to low values of Carrington longitudes (right to left along the X-axis) and from bottom to top along the Y-axis [Taken from Plotnikov et al. 2015] Eduardo Sanchez-Diaz (recruited in Nov. 2014); has investigated the speed of small transients in HI and has found that they have very slow speeds, that these small-scale transients retain very slow speeds up to 0.3-0.4AU and investigated whether HELIOS-measured such low speeds in solar cycle 22. These speeds are indeed measured in situ up to 0.6 AU, this provided additional confidence that our speed calculations are correct. A paper was submitted to Geophysical Research Letters but after a mitigated referee report mainly due to suitability of the paper for the GRL format, we decided to re-submit to JGR. Eduardo has identified times when blobs emitted from the corona observed in STEREO-A images are propagating towards STEREO-B and L1, he is currently analysing this data. We note two papers related with the HELCATS work in this WP: Sanchez-Diaz, E., Segura, K., Rouillard, A.P., Lavraud, B., Chihiro T., The very slow solar wind: origin, variability and properties, to be submitted to JGR, 2015. Plotnikov, I., Rouillard, A.P., Davies, J.A. et al., Long-term tracking of corotating density structures using heliospheric imaging, to be submitted shortly to Solar Physics, 2015

WORK PACKAGE 6 (WP6): Initialising advanced numerical models based on the kinetic properties of STEREO/HI CMEs and CIRs

WP6 ACTIVITY TYPE: UPS

WP6 DURATION: MONTHS 7 – 36

WP6 LEAD BENEFITIARY: UPS (1)

WP6 LEADER: Dr Alexis Rouillard

WP6 CONTRUBUTORS: GMU

WP6 OVERVIEW: The primary goal of WP6 is to transform the catalogues of CMEs and CIRs observed by HI, accomplished in WP2/3 and WP5, into more advanced catalogues of simulations results of CIRs and CMEs. This advanced database will provide to the space community a set of simulation results optimised by assimilating direct images of the solar wind into ENLIL simulations. The delivery of these advanced catalogues will enhance forefront research on the ‘background’ solar wind (fast and slow solar wind) and on the spatial and temporal evolution of CIRs and CME shocks, and will provide unique material to study and interpret particle radiation measurements in the inner heliosphere.

We have addressed a subset of the goals of the four tasks defined for WP5, namely: T6.1 - Assimilating HI images to model the background solar wind [Months: 7-36] UPS The combination of the catalogues of CIRs derived in WP5.1 and WP5.2, J-maps derived from HI images and movies has been compared with preliminary synthetic J-maps of CIRs derived from numerical simulations of the background solar wind (ENLIL) through the propagation tool. We are currently dividing events in two classes: Class 1 for which a good correspondence is immediately obtained between simulated and observed height-time maps and Class 2 for which J-maps differ significantly. Since the annual report, Rui Pinto has enabled his solar wind code to use different magnetogram sources (Wilcox Solar Observatory, Mount Wilson and Solar Dynamics Observatory) to produce potential field source surface (PFSS) maps of the coronal magnetic field. The use of other methods of coronal field reconstruction (e.g, non-linear force-free methods) is also possible. His model calculates an ensemble of solar wind profiles on a large sample of open magnetic flux-tubes covering all solar latitudes and longitudes. The wind solutions cover all the heights ranging from the surface up to about 30 solar radii (including the chromosphere and the transition region). Fig 6.1: A sample of magnetic field-lines (in blue) extrapolated from an SDO surface magnetogram (grey-scale map over the solar surface) corresponding to the Carrington rotation 2137 used for fine-tuning the solar wind model and already present on the S/CIR catalogue (WP5). He has pursued his numerical effort to produce Carrington Maps of solar wind parameters at 21.5Rs to initialise ENLIL. He has run his solar wind model for several consecutive Carrington rotations (so far covering the year 2009), in addition to a later case present in the catalogue of Corotating Density Structures (S/CIRs) from WP5 (Carrington rotation 2137, May-June 2013). He is currently using these solutions to fine-tune and and validate the model against in-situ data from OMNI at 1 AU (especially the case from 2013, which displays a highly warped helispheric current sheet and an intricate mixture of fast and slow wind flows). The model already produces good quality predictions for the wind speed and temperature, and the fine-tuning in progress is leading to improvements on the predictions of the density of the wind flows (which is a common difficulty for all current day solar wind models). Additional sources of calibration come from detection of Alfvén wave propagation within the wind flows at the lowest-lying layers of the corona, as described in: Morton, Tomczyk, Pinto, Nature Communications, Volume 6, 7813 (2015). The developments undertaken under the scope of this task also led to the two following papers (to be submitted soon): Pinto, R., Brun, S., Rouillard, A.P., Wang, Y.-M., The slow and fast wind during an activity cycle, to be submitted to Astrophys. Journal, 2015. Pinto, R., Rouillard, A.P., Wang, Y.-M., Grappin, R. The acceleration of the solar wind along magnetic flux tubes of varying geometries, to be submitted to Astrophys. J., 2015. We have furthermore started comparing our own PFSS reconstructions based on Wilcox Solar Observatory data with those using SDO data (obtained via SolarSoft), and the first results suggest that one of the key parameters for PFSS extrapolations (the height of the source-surface) should be re-evaluated for more realistic results. Fig. XX1 shows a series of magnetic field-lines calculated via PFSS for one of the Carrington rotations tested. The outcome of the model comes in the form of a series of maps of wind speed, temperature and density for all Carrington latitudes and longitudes at 21.5 solar radii (see example in Fig. 6.2). Rui Pinto defined a longitude-latitude grid with variable angular resolution (δθ = 2.5°, 5° and 10°, respectively on the equatorial, mid-latitude and high-latitude regions) that corresponds roughly to an uniform spatial coverage over the sphere. The set of maps can be completed at the highest resolution, if necessary. Fig 6.2: Maps of the calculated wind speed (first panel, in blue) and temperature (second panel, in red) at 32 Rs for the Carrington rotation 2137 (represented in Fig XX1). The X-axis represents solar longitude and the Y-axis represents solar latitude. T6.2 - Assessing the use of HI to initialize ENLIL [Months: 7-36] UPS Since the annual report, we have read the catalogues produced by WP3 to locate CMEs relative to CIRs/SIRs by projecting their trajectories on the source surface. We are also comparing the 3-D trajectory of CME derived from WP3 with the trajectory of CMEs located by the NOAA alert system and available through synthetic J-maps derived by the ENLIL model. We are also evaluating the latitudinal extent that will have to be considered for the injection of CMEs in the MHD model. The synthetic J-maps are produced by computing the white-light heliospheric images that STEREO-A and STEREO-B should see from their vantage points. These images are derived by applying the equations of Thomson scattering from the simulated 3-D volume of electronic densities. The code computes running-difference images and like ordinary J-maps, a band of pixels is extracted along the ecliptic plane. These J-maps have so far been produced for 2012 and 2013. We integrated them in our software tool and can switch from these maps to real J-maps. In the tool, we can now superpose the catalogue of J-maps derived in WP5. This allows us to compare the trajectories and patterns left by CIRs derived from observations with the trajectories of CIRs derived from numerical simulations. T6.3 - Continual assimilation of HI data in ENLIL and comparison with standard implementation techniques [Months: 7-36] We will start this task in Month 24. Other papers in preparation: Rouillard, A.P., Plotnikov, I., R. Pinto,… ,The expansion of coronal pressure waves in 3-D during Coronal Mass Ejections, to be submitted to Astrophysical Journal, 2015.

WORK PACKAGE 8 (WP8): PRODUCING A DEFINITIVE CATALOGUE OF CIRs IMAGED BY STEREO/HI THAT INCLUES VERIFIED MODEL-DERIVED KINEMATIC PROPERTIES

WP6 ACTIVITY TYPE: STFC

WP6 DURATION: MONTHS 1 – 36

WP6 LEAD BENEFITIARY: STFC (1)

WP6 LEADER: Dr Chris Perry

WP6 CONTRUBUTORS: IRAP

IRAP contribution: TASK 8.1- Publication of results and conclusions [Months: 1-36] - The work carried out by the IRAP is leading to four papers that have and will be submitted over the next two months. One on the presence of a very slow solar wind (1st author: submitted by Eudardo Sanchez-Diaz), one paper on the statistical properties of CIRs tracked in HI and their relation with in-situ measurements (1st author to be submitted by Illya Plotnikov), one paper on the influence of magnetic field line topology in the low corona on the terminal speed of the solar wind (1st author not yet submitted by Rui Pinto), one paper on the extent of coronal shock waves observed in white-light images (1st author not yet submitted by Alexis Rouillard). TASK 8.2 - Annual open meetings with the science community and presentations at major science meetings [Months: 1-36] - Eduardo Sanchez-Diaz has presented his results on the very slow solar wind at EGU in April 2015 and at the L ‘Aquila summer school in September 2015. - Rui Pinto showed the results of work on solar wind acceleration at the AIC meeting in Tampa, Florida in April 2015 and as an invited talk at the Solar Wind 14 meeting in Weihai. Alexis Rouillard presented his work in an invited talk at the IUGG in Prague and the 1st Solar Orbiter/Solar Probe+ meeting in Florence. TASK 8.4- Publication of results and conclusions [Months: 1-36] - The IRAP catalogues are being produced in both .xml format (VOtables) and .ascii readable by most computing languages. - The CIR catalogue developed in WP5 has been integrated in the ‘propagation tool’ (propagationtool.cdpp.eu). This has required some modification of the tool that was supervised by Alexis Rouillard. We are currently integrating the CME catalogue produce by WP2 for both the fixed point and the harmonic mean techniques. This should be operational in the coming weeks. The next step will be to create a webservice between our tools and the source archive of all these catalogues at STFC. - We have also integrated ENLIL simulations to the propagationtool.cdpp.eu so that the community can also have access to these synthetic J-maps. - The CME catalogues produced in WP3 with the fixed phi and harmonic mean techniques have been integrated in the propagationtool.cdpp.eu and this is used in WP6.